## Slide 1: Transition Management Office Projects
 |  | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | PM | RM
Application Relocation | Data Center Realignment |  |  |  |  |  |  | N Longo D Oliver | R Francis K Emery S Bryant
 | VU Off-Site Data Center |  |  |  |  |  |  | J Wolff | K Emery
Infrastructure Separation | VU ITSM |  |  |  |  |  |  | D Oliver | C Contos
 | Data Network |  |  |  |  |  |  | C Marshall | J McCammon M Hollifield S Bryant
 | Voice Network |  |  |  |  |  |  | C Stevenson | K McGill-Barrett J Giampaolo S Bryant L Smith L Byrd
Identity and Application Separation | VUMC Unified Communications |  |  |  |  |  |  | L Beckett | J Smith K King
 | VUMC Email |  |  |  |  |  |  | L Beckett | J Osborne S Bryant L Smith
 | VUMC Directory Services |  |  |  |  |  |  | R Williams | L Smith
 | VU Directory Services |  |  |  |  |  |  | R Williams | J Loudon M Hollifield
 | VU Master Data Management |  |  |  |  |  |  | D Platz | R Francis C Contos
 | VU Identity Management |  |  |  |  |  |  | D Platz | R Francis C Contos
 | VU SkyVU |  |  |  |  |  |  | N Oeser | K Emery J Smith
 | Vu Business Intelligence |  |  |  |  |  |  | A Jacob | 
 | Couch Stabilization |  |  |  |  |  |  |  | 
Phase 1: Relocate dev, test, & prod
Build out dev and
test infrastructure
XL
Build out prod
infrastructure
M
VUH back-up
IR, storage
M
M
S
Analysis II
Build
Dev
Skype / IP Migration
Skype
primary & secondary
environment build
Skype
user migration
Skype
analysis
Voice separation
Build out Lync
2013 in VUH
XL
M
Analysis
BI replacement
New IDM implementation
*IDM requires operational VU DS shell April 2017
EPI replacement implementation
MDM – additional data
SkyVU implementation
Analysis
Domain name decision
VUMC email service transition
*VUMC email requires operational VUMC DS
Analysis
Separate network cores and control point
Separate VPN
Separate perimeter and security environment
Establish new
brick and mortar
secondary DC
Demos
IDM vendor
selection
(SailPoint)
MDM vendor
selection
(IBM)
Building
realign
S
XL
L
M
XS
XS
L
M
XS
L
XS
L
L
XL
M
L
Migrate users, applications, and workstations to new directory services
M
M
M
XL
Migrate users, applications, and workstations to new directory services
XL
vumc.org primary
L
November, 2017
Epic Leap Go-Live
Jan. 1, 2018
SkyVU Go-Live
XS
M
M
Oracle upgrade for PS HR
AccessVU and EPI patching
Oracle HCM
Part II
S
Separate wireless
L
Shared DS Upgrade
L
M
Phase 2: Data feeds / Data connections
L
E
Sizing of effort
completed
Today
Phase 1
Change & Config
Phase 2
Incident, Request, Asset
Phase 3
Problem & Knowledge
L
Build (Dev, Test, Prod)
Build (Dev, Test, Prod)
Build
Test
Build
Prod
M
M
Build
Dev
M
Build
Test
Build
Prod
M
M